## Sheet1
System Design Block Table for Pick and Place Robot System
Sybsystem | Block Name | Description | Est. Cost | Est. Date Complete | Developer Name(s)
Software | Arduino Pick Code | Arduino Code for robot to pick a shape | Free | 2016-10-12 | Kurtis Rickelmann
| PC C# Pick Code | C# Code for robot to pick a shape | Free | 2016-10-12 | Kurtis Rickelmann
| Arduino Pick n Place Code | Arduino Code for robot to pick and place a shape | Free | 2016-12-07 | Kurtis Rickelmann
| PC C# Pick n Place Code | C# Code for robot to pick and place a shape | Free | 2016-12-07 | Kurtis Rickelmann
Hardware | Robot Structure | 3D-printed mechanical structure of the robot | 20 | 2016-09-30 | Kurtis Rickelmann
| Servo/Stepper Motor | Servo or Stepper Motor for the rotation of the robot base (undecided) | 10 | 2016-09-25 | TowerPro
| Servo Motor | Servo Motors for the rotation of the arms (x2) | 20 | 2016-09-26 | TowerPro
| Electromagnet | Electromagnet to pick up the metal shapes | 5 | 2016-10-15 | N/A
| Arduino Uno R3 | Arduino Dev board for controlling robot arm | 8 | Done | Arduino
| Sainsmart Motor Shield | Arduino Shield for controlling motors | 6 | Done | Sainsmart
| USB Camera | Camera to capture picture of where the shapes are | 10 | 2016-09-30 | N/A